## Slide 1
SUPPLY CHAIN
Cost Optimization
Management Consulting Case | Synthetic Portfolio Project

## Slide 2
Executive message
Build a transparent cost baseline before targeting savings.
Focus first on procurement, freight and inventory value pools.
Prioritize initiatives using impact, feasibility, speed and confidence—not theoretical savings alone.
Validate savings through RFQs, freight tenders, inventory pilots and Finance sign-off.
Use a 90-day launch program followed by a rolling 12-month savings pipeline.

## Slide 3
Cost baseline
Cost pool | Illustrative baseline | Main driver
Procurement | ₹1,083 cr | Price × volume
Inbound freight | ₹40 cr | Lane rate × shipments
Inventory carrying | ₹88.8 cr | Inventory × carrying rate
All transaction-level values are synthetic case data.
The purpose is to demonstrate the consulting cost-diagnostic methodology.

## Slide 4
Savings portfolio
Initiative | Gross | Implementation | Net
Steel negotiation | ₹18.0 cr | ₹2.0 cr | ₹16.0 cr
Electronics sourcing | ₹12.0 cr | ₹4.0 cr | ₹8.0 cr
Freight consolidation | ₹8.0 cr | ₹1.0 cr | ₹7.0 cr
Mode optimization | ₹5.0 cr | ₹1.5 cr | ₹3.5 cr
Inventory parameters | ₹10.0 cr | ₹2.0 cr | ₹8.0 cr
Slow-moving inventory | ₹6.0 cr | ₹1.0 cr | ₹5.0 cr

## Slide 5
Where to act
Procurement: benchmark prices, run competitive sourcing and consolidate volume where practical.
Logistics: tender high-cost lanes, consolidate shipments and assess alternative modes.
Inventory: reset safety stock/reorder parameters and reduce slow-moving stock.
Governance: track realized savings monthly and protect service, quality and continuity.

## Slide 6
90-day implementation
Period | Priority actions
0–30 days | Validate baseline, benchmark prices, review lanes and inventory aging
31–60 days | Run sourcing events, freight tender and inventory parameter redesign
61–90 days | Award suppliers/carriers, launch pilots and track realized benefits
3–12 months | Scale validated initiatives and build next-wave savings pipeline

## Slide 7
Management conclusion
The cost opportunity is best addressed as a coordinated procurement, logistics and inventory program.
Start with high-confidence initiatives while validating larger or technically constrained opportunities.
Savings should only be recognized when operationally realized and Finance-validated.
A disciplined governance cadence can convert one-time initiatives into a repeatable cost-transformation capability.